## Sheet1
NOTICE REF | Address Work Details (Inc Postcode) | Postcode | Location | Traffic Control | Notice Days | Work Status | Estimated Start Date | Latest/Actual Start Date | Estimated End Date
K080-GC/28601940/01 | SEAGRY ROAD SUTTON BENGER | SN15 4RX | FW CW VERGE THE WHOLE OF SEAGRY ROAD SUTTON BENGER | Traffic Control (Two-Way Signals) | 3 Days | In Progress | 2019-12-13 | 2019-12-16 | 2019-12-18
K080-GC/28602132 | HIGH STREET, SUTTON BENGER | SN15 4RQ | FW CW VERGE THE WHOLE OF HIGH STREET | Traffic Control (Two-Way Signals) | 10 Days | Initial Notice/Permit | 2020-01-06 | 2020-01-10 | 2020-01-17
K080-GC/28601634 | SEAGRY HILL, SUTTON BENGER | SN15 4SA | FW CW VERGE THE WHOLE OF SEAGRY HILL | Traffic Control (Two-Way Signals) | 10 Days | Initial Notice/Permit | 2020-01-07 | 2020-01-13 | 2020-01-20
K080-GC/28601940 | SEAGRY ROAD SUTTON BENGER | SN15 4RX | FW CW VERGE THE WHOLE OF SEAGRY ROAD SUTTON BENGER | Traffic Control (Two-Way Signals) | 10 Days | Initial Notice/Permit | 2020-01-08 | 2020-01-14 | 2020-01-21
K080-GC/28601999 | B4122 TO HIGH STREET, DRAYCOT CERNE |  | FW CW VERGE THE WHOLE OF B4122 TO HIGH STREET | Traffic Control (Two-Way Signals) | 10 Days | Initial Notice/Permit | 2020-01-10 | 2020-01-16 | 2020-01-23
K080-GC/28602001 | JCT 17 M4 TO B4069 B4122 |  | FW CW VERGE THE WHOLE OF JCT 17 M4 TO B4069 B4122 | Traffic Control (Two-Way Signals) | 10 Days | Initial Notice/Permit | 2020-01-13 | 2020-01-17 | 2020-01-24
K080-GC/28601635 | SEAGRY ROAD, SUTTON BENGER | SN15 4RX | FW CW VERGE THE WHOLE OF SEAGRY ROAD | Road Closure | 3 Months | Initial Notice/Permit | 2020-03-23 | 2020-03-27 | 2020-04-06
K080-GC/44200450 | (DAYS LANE) NEWLANDS GREEN NORTH C171 TO JUNCTION WITH A350 |  | FW CW VERGE THE WHOLE OF NEWLANDS GREEN NORTH C171 TO JUNCTION WITH A350 | Road Closure | 3 Months | Initial Notice/Permit | 2020-03-30 | 2020-04-03 | 2020-04-15
K080-GC/28601636 | SUTTON LANE, SEATON BENGER | SN15 4RR | FW CW VERGE THE WHOLE OF SUTTON LANE | Road Closure | 3 Months | Initial Notice/Permit | 2020-04-06 | 2020-04-10 | 2020-04-22