## Sheet1
Address Work Details (Inc Postcode) | Traffic Control | Work Status | Estimated Start Date | Latest/Actual Start Date | Estimated End Date
HIGH STREET, SUTTON BENGER | Traffic Control (Two-Way Signals) | Work Stop | 2020-01-06 | 2020-01-10 | 2020-01-17
SEAGRY HILL, SUTTON BENGER | Traffic Control (Two-Way Signals) | Work Stop | 2020-01-07 | 2020-01-13 | 2020-01-20
SEAGRY ROAD SUTTON BENGER | Traffic Control (Two-Way Signals) | In Progress | 2020-01-08 | 2020-01-14 | 2020-01-21
B4122 TO HIGH STREET, DRAYCOT CERNE | Traffic Control (Two-Way Signals) | Initial Notice/Permit | 2020-01-10 | 2020-01-16 | 2020-01-23
JCT 17 M4 TO B4069 B4122 | Traffic Control (Two-Way Signals) | Initial Notice/Permit | 2020-01-20 | 2020-01-23 | 2020-01-31
SEAGRY ROAD, SUTTON BENGER | Road Closure | Initial Notice/Permit | 2020-03-23 | 2020-03-27 | 2020-04-06
(DAYS LANE) NEWLANDS GREEN NORTH C171 TO JUNCTION WITH A350 | Road Closure | Initial Notice/Permit | 2020-03-30 | 2020-04-03 | 2020-04-15
SUTTON LANE, SEATON BENGER | Road Closure | Initial Notice/Permit | 2020-04-06 | 2020-04-10 | 2020-04-22